## Sheet1
S.No.	Description	Status	Date Done	Comments
1	Write and get the description of signals in PXTU Module.	Done	03/11/17
2	Update the CSV with signal's description	Done	03/11/17
3	Modify createDB.py to create file and update without depending on the current DB file
4	Create a diagnostics for error finder and a provision to auto correct			#16 should fix what is required
5	Make the IP obtaining from the XML file rather than hardcoding it	Done	06/24/17	Tested working but needs improvement
6	Make a time stamp feature in arduino engine for data exchange between arduino and pi.	Done	06/11/17	To be tested with integration to arduino.
7	Add capability for not writing to SHM when it is locked.
8	Write frequency of every engine into the SHM
9	Create master controller to the source	Done	06/17/17
10	Master controller should check the input status of the engine and run accordingly	Done	06/17/17
11	Make RTU and Dcap as Daemons			Dcap not working in Daemon needs debugging
12	Change couts to logger for RTU
13	Implement engine controller in Python (like base)	Done	06/26/17	like robot.engine.arduino.state = 1/0
14	Create a data capture engine that can be used for recording the data	Done	06/24/17	Tested working
15	In sync with the #14, create an evaluation Python lib that can evaluate timing and others	Done	06/24/17	Tested working
16	Add code to arduino engine to reset the Arduino base when it is stuck in some condition.			Reset the timestamp counter
17	Make bash for building all the engines and common
18	Learn GPIO pin programming in Linux
19	Add namespace to falcon			Create a new namespace in shared library
20	Fix Cmake for Windows without affecting Linux	Done	07/20/17	cmake works in windows now for engines and common
21	Add ms to the dcap timestamp	Done	06/26/17	These are the units of the recording time
22	Add feature for checking the status and then running	Done	06/26/17	If the engine is paused, the master should not run
23	Add a feature to PXTU to exit all the running engine on the Pi			It should kill all the engines including RTU and Dcap Use #25
24	Implement as a thread in engineFrame to do some engine specific background tasks			It should do #23. Use #25
25	Create a new variable for EXIT engines			EngineFrame thread should monitor this variable and exit when set
26	Dcap engine shall send an ACK for its request	Done	07/19/17
27	Create ways to evaluate the CSV file
28	Give a static IP to the target			192.168.0.143
29
30

## Low Priority
Create thread in master engine for transmitting the data to LabView GUI.- LP			Check detailed description
Create LabView GUI with initial draft of lights.- LP