## Sheet1
S.No.	Description	Status	Date Done	Comments
1	Write and get the description of signals in PXTU Module.	Done	03/11/17
2	Update the CSV with signal's description	Done	03/11/17
3	Modify createDB.py to create file and update without depending on the current DB file
4	Create a diagnostics for error finder and a provision to auto correct			#16 should fix what is required
5	Make the IP obtaining from the XML file rather than hardcoding it	Done	06/24/17	Tested working but needs improvement
6	Make a time stamp feature in arduino engine for data exchange between arduino and pi.	Done	06/11/17	To be tested with integration to arduino.
7	Add capability for not writing to SHM when it is locked.
8	Write frequency of every engine into the SHM
9	Create master controller to the source	Done	06/17/17
10	Master controller should check the input status of the engine and run accordingly	Done	06/17/17
11	Create thread in master engine for transmitting the data to LabView GUI.- LP			Check detailed description
12	Create LabView GUI with initial draft of lights.- LP
13	Implement engine controller in Python (like base)	Done	06/26/17	like robot.engine.arduino.state = 1/0
14	Create a data capture engine that can be used for recording the data	Done	06/24/17	Tested working
15	In sync with the #14, create an evaluation Python lib that can evaluate timing and others	Done	06/24/17	Tested working
16	Add code to arduino engine to reset the Arduino base when it is stuck in some condition.			Reset the timestamp counter
17	Make bash for building all the engines
18	Learn GPIO pin programming in Linux
19	Add namespace to falcon			Create a new namespace in shared library
20	Make the dcap engine return something to the PXTU on successfully starting to write			Just to know the ACK status
21	Add ms to the dcap timestamp	Done	06/26/17	These are the units of the recording time
22	Add feature for checking the status and then running	Done	06/26/17	If the engine is paused, the master should not run
23
24
25
26
27
28
29
30