## Sheet1
S.No.	Description	Status	Date Done	Comments
1	Write and get the description of signals in PXTU Module.	Done	03/11/17
2	Update the CSV with signal's description	Done	03/11/17
3	Modify createDB.py to create file and update without depending on the current DB file
4	Create a diagnostics for error finder and a provision to auto correct
5	Make the IP obtaining from the XML file rather than hardcoding it
6	Make a time stamp feature in arduino engine for data exchange between arduino and pi.	Done	06/11/17	To be tested with integration to arduino.
7	Add capability for not writing to SHM when it is locked.
8	Write frequency of every engine into the SHM
9
10
11	Create thread in master engine for transmitting the data to LabView GUI.			Check detailed description
12	Create LabView GUI with initial draft of lights
13
14
15
16
17
18
19
20
21
22