## Sheet1
S.No.	Description	Status	Date Done	Comments
1	Write and get the description of signals in PXTU Module.	Done	03/11/17
2	Update the CSV with signal's description	Done	03/11/17
3	Modify createDB.py to create file and update without depending on the current DB file
4	Create a diagnostics for error finder and a provision to auto correct
5	Make the IP obtaining from the XML file rather than hardcoding it
6	Make a time stamp feature in arduino engine for data exchange between arduino and pi.	Done	06/11/17	To be tested with integration to arduino.
7	Add capability for not writing to SHM when it is locked.
8	Write frequency of every engine into the SHM
9	Create master controller to the source	Done	06/17/17
10	Master controller should check the input status of the engine and run accordingly
11	Create thread in master engine for transmitting the data to LabView GUI.- LP			Check detailed description
12	Create LabView GUI with initial draft of lights.- LP
13	Implement engine controller in Python (like base)			like robot.engine.arduino.state = 1/0
14	Create a data capture engine that can be used for recording the data
15	In sync with the #14, create an evaluation Python lib that can evaluate timing and others
16
17
18
19
20
21
22